## Sheet1
APCERE Requirements
Requirement | Completed | Partial Completion | Not Started | Comment | Risks
Detect EL
notify embedded linux of EL
Operate under battery Power |  |  |  |  | Has never been constraint
display embedded linux error codes
PID |  |  |  | Previous Must | Was left out previosly
Heartbeat |  |  |  | Previous Should | Was left out previosly, Requires major code restructuring
APCEL Requirements
Requirement | Completed | Partial Completion | Not Started | Comment | Risks
collect sensor data from X sensor
collect sensor data from Y sensor
collect sensor data from Z sensor
operates from bench supply
Display Sensor Data |  |  |  | Assumes LCD on Board
Convert signal into formtatted data (units)
Platform Supervisor Requirements
Requirement | Completed | Partial Completion | Not Started | Comment | Risks
establish communication with embedded linux through socket via wifi |  |  |  |  | Never worked with wifi, limited network experience
display video stream from robot webcam |  |  |  |  | Never worked with video
display EL data
send commands to embedded linux
Embedded linux Requirements
Requirement | Completed | Partial Completion | Not Started | Comment | Risks
establlish connection with supervisor through socket via wifi |  |  |  |  | Never worked with wifi, limited network experience
send video stream from robot webcam to supervisor |  |  |  |  | Never worked with video
operate webcam
data retrieval from EL (simulated)
error checking with supervisor
error checking with platform controller
indicate EL data retrievel to supervisor
receive commands from supervisor |  |  |  |  | Potential Multi-threaded code required